# Comprehensive Equipment Schedule Risk Analysis

## 1. Executive Summary

- Overall Risk Levels: Medium Risk (1 item), Low Risk (2 items), High Risk (0 items), On-Track (0 items).

- Key Findings:

  - Medium Risk item identified due to early delivery, which may lead to storage and handling issues.

  - Low Risk items have minimal impact but require monitoring.

- Total Equipment Analyzed: 3

## 2. Comprehensive Risk Summary Table

### a. Executive Summary

- Total Items Analyzed: 3

- Risk Breakdown:

  - High Risk: 0 items

  - Medium Risk: 1 item

  - Low Risk: 2 items

  - On-Track: 0 items

### b. Equipment Comparison Table

| Equipment Code | Equipment Name | P6 Due Date | Delivery Date | Variance (days) | Risk % | Risk Level | Manufacturing Country | Project Country |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | 10.44 | Medium Risk | USA | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | 1.66 | Low Risk | China | Germany |
| 123458 | LV Switchgear - 400V/5000A Switchboard-3 (3-Sections) | 2026-02-27 | 2026-03-07 | +8 | 2.64 | Low Risk | Philippines | Germany |

### c. High Risk Items

- None Identified

### d. Medium Risk Items

#### Equipment: LV Switchgear - 400V/5000A Switchboard-1 (3-Sections)

- Code: 123456

- Variance: -31 days (Early)

- Risk %: 10.44%

- Manufacturing Location: USA

- Impact: Early delivery may lead to storage and handling issues at the site.

- Contributing Factors: Supplier lead time shorter than anticipated.

- Downstream Effects: Potential for increased storage costs and handling risks.

- Mitigation Actions:

  - Confirm readiness of site to accept early delivery.

  - Coordinate with supplier to adjust delivery timelines if possible.

  - Ensure proper storage facilities are available.

### e. Low Risk Items

#### Equipment: LV Switchgear - 400V/5000A Switchboard-2 (3-Sections)

- Code: 123457

- Variance: -5 days (Early)

- Risk %: 1.66%

- Manufacturing Location: China

- Impact: Minimal impact expected.

- Mitigation Actions:

  - Maintain current schedule adherence.

  - Monitor for any potential delays.

#### Equipment: LV Switchgear - 400V/5000A Switchboard-3 (3-Sections)

- Code: 123458

- Variance: +8 days (Late)

- Risk %: 2.64%

- Manufacturing Location: Philippines

- Impact: Minimal impact expected.

- Mitigation Actions:

  - Maintain current schedule adherence.

  - Monitor for any potential delays.

### f. On-Track Items

- None Identified

### g. Recommendations

- Medium Risk Items:

  - Monitor closely and ensure early delivery does not cause storage or handling issues.

  - Coordinate with the supplier to confirm readiness for site delivery.

- Low Risk Items:

  - Maintain current schedule adherence.

  - Monitor for any potential delays.

No immediate actions are required for High Risk or On-Track categories as none were identified.

## 3. Detailed Risk Analysis by Category

### A. Schedule Risk Analysis

#### High Risk Items

- None Identified

#### Medium Risk Items

- LV Switchgear - 400V/5000A Switchboard-1 (3-Sections):

  - Early delivery by 31 days.

  - Risk %: 10.44%.

  - Mitigation Actions: Confirm site readiness, coordinate with supplier, ensure proper storage facilities.

#### Low Risk Items

- LV Switchgear - 400V/5000A Switchboard-2 (3-Sections):

  - Early delivery by 5 days.

  - Risk %: 1.66%.

  - Mitigation Actions: Maintain schedule adherence, monitor for delays.

- LV Switchgear - 400V/5000A Switchboard-3 (3-Sections):

  - Late delivery by 8 days.

  - Risk %: 2.64%.

  - Mitigation Actions: Maintain schedule adherence, monitor for delays.

## 4. Consolidated Recommendations

- Medium Risk Items:

  - Confirm readiness of site to accept early delivery.

  - Coordinate with supplier to adjust delivery timelines if possible.

  - Ensure proper storage facilities are available.

- Low Risk Items:

  - Maintain current schedule adherence.

  - Monitor for any potential delays.

- General Recommendations:

  - Establish a robust monitoring system for all equipment deliveries.

  - Enhance communication with suppliers to mitigate early or late deliveries.