# Comprehensive Equipment Schedule Risk Analysis

## 1. Executive Summary

- Overall Risk Levels:

  - Medium Risk: 1 item

  - Low Risk: 2 items

  - High Risk: None

  - On-Track: None

- Key Findings:

  - Medium-risk item identified with early delivery requiring mitigation actions.

  - Low-risk items have minor variances with minimal impact.

- Total Equipment Analyzed: 3

## 2. Comprehensive Risk Summary Table

### a. Executive Summary

- Total Items Analyzed: 3

- Risk Breakdown:

  - Medium Risk: 1 item

  - Low Risk: 2 items

  - High Risk: None

  - On-Track: None

### b. Equipment Comparison Table

| Equipment Code | Equipment Name | P6 Due Date | Delivery Date | Variance (days) | Risk % | Risk Level | Manufacturing Country | Project Country |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | 10.44 | Medium Risk | USA | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | 1.66 | Low Risk | China | Germany |
| 123458 | LV Switchgear - 400V/5000A Switchboard-3 (3-Sections) | 2026-02-27 | 2026-03-07 | 8 | 2.64 | Low Risk | Philippines | Germany |

### c. High Risk Items

- None identified.

### d. Medium Risk Items

#### Equipment Code: 123456

- Equipment Name: LV Switchgear - 400V/5000A Switchboard-1 (3-Sections)

- Variance: -31 days (EARLY)

- Risk %: 10.44%

- Impact: Early delivery may require storage arrangements and additional costs. Coordination with site readiness is critical.

- Factors Contributing to Variance: Supplier lead time optimization and expedited logistics.

- Potential Downstream Effects: Increased storage costs and potential misalignment with project readiness.

- Recommended Mitigation Actions:

  - Confirm site readiness for early delivery.

  - Coordinate with supplier and logistics teams to adjust delivery timing if necessary.

  - Monitor storage costs and ensure proper handling.

### e. Low Risk Items

#### Equipment Code: 123457

- Equipment Name: LV Switchgear - 400V/5000A Switchboard-2 (3-Sections)

- Variance: -5 days (EARLY)

- Risk %: 1.66%

- Impact: Minimal impact due to slight early delivery.

- Factors Contributing to Variance: Efficient logistics and supplier adherence to schedule.

- Recommended Mitigation Actions:

  - Maintain regular updates with supplier.

  - Ensure site readiness for early delivery.

#### Equipment Code: 123458

- Equipment Name: LV Switchgear - 400V/5000A Switchboard-3 (3-Sections)

- Variance: 8 days (LATE)

- Risk %: 2.64%

- Impact: Slight delay unlikely to affect overall project timeline.

- Factors Contributing to Variance: Minor logistics delays.

- Recommended Mitigation Actions:

  - Monitor logistics closely to avoid further delays.

  - Ensure no cascading effects on subsequent project milestones.

### f. On-Track Items

- None identified.

### g. Recommendations

- Medium Risk (Equipment 123456):

  - Coordinate with supplier and logistics teams to align delivery with site readiness.

  - Monitor storage costs and ensure proper handling.

- Low Risk (Equipment 123457 and 123458):

  - Maintain regular updates with suppliers.

  - Monitor logistics to avoid further delays.

## 3. Detailed Risk Analysis by Category

### A. Schedule Risk Analysis

#### High Risk Items

- None identified.

#### Medium Risk Items

- Equipment Code: 123456

  - Variance: -31 days (EARLY)

  - Risk %: 10.44%

  - Impact: Early delivery may require storage arrangements and additional costs. Coordination with site readiness is critical.

  - Recommended Mitigation Actions:

    - Confirm site readiness for early delivery.

    - Coordinate with supplier and logistics teams to adjust delivery timing if necessary.

    - Monitor storage costs and ensure proper handling.

#### Low Risk Items

- Equipment Code: 123457

  - Variance: -5 days (EARLY)

  - Risk %: 1.66%

  - Impact: Minimal impact due to slight early delivery.

  - Recommended Mitigation Actions:

    - Maintain regular updates with supplier.

    - Ensure site readiness for early delivery.

- Equipment Code: 123458

  - Variance: 8 days (LATE)

  - Risk %: 2.64%

  - Impact: Slight delay unlikely to affect overall project timeline.

  - Recommended Mitigation Actions:

    - Monitor logistics closely to avoid further delays.

    - Ensure no cascading effects on subsequent project milestones.

## 4. Consolidated Recommendations

### a. Medium Risk (Equipment 123456):

- Coordinate with supplier and logistics teams to align delivery with site readiness.

- Monitor storage costs and ensure proper handling.

### b. Low Risk (Equipment 123457 and 123458):

- Maintain regular updates with suppliers.

- Monitor logistics to avoid further delays.