# Comprehensive Equipment Schedule Risk Analysis

## 1. Executive Summary

- Overall Risk Levels: The analysis identified risks across schedule, political, tariff, and logistics categories. Political risks are notably high in certain regions, while schedule risks are primarily medium to low.

- Key Findings:

  - High political risks in USA-China trade sanctions and Philippines-China geopolitical tensions.

  - Medium schedule risks for equipment originating from the USA and India.

  - Low schedule risks for equipment from the UK, China, and Malaysia

- Total Equipment Analyzed: 6

  - High Risk: 2 items.

  - Medium Risk: 2 items.

  - Low Risk: 2 items.

## 2. Comprehensive Risk Summary Table

### a. Executive Summary

- Total Items Analyzed: 6

- Risk Breakdown:

  - High Risk: 2 items

  - Medium Risk: 2 item

  - Low Risk: 2 items

  - On-Track: 0 items

### b. Equipment Comparison Table

| Equipment Code | Equipment Name | P6 Due Date | Delivery Date | Variance (days) | Risk % | Risk Level | Manufacturing Country | Project Country |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | 10.44 | Medium Risk | USA | Germany |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | 10.44 | Medium Risk | India | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | 1.66 | Low Risk | China | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | 1.66 | Low Risk | UK | Germany |
| 123458 | LV Switchgear - 400V/5000A Switchboard-3 (3-Sections) | 2026-02-27 | 2026-03-07 | +8 | 2.64 | Low Risk | Philippines | Germany |
| 123458 | LV Switchgear - 400V/5000A Switchboard-3 (3-Sections) | 2026-02-27 | 2026-03-07 | +8 | 2.64 | Low Risk | Malaysia | Germany |

### c. High Risk Items

- USA-China Trade Sanctions: Could delay shipments originating from the USA due to export restrictions.

- Philippines-China Geopolitical Tensions: May disrupt shipping routes from the Philippines

### d. Medium Risk Items

- India-Germany Tariff Disputes: Potential cost increases or delays for equipment from India.

- Malaysia Labor Strikes: Could slow down production timelines.

### e. Low Risk Items

- UK Regulatory Changes: Minimal impact expected as post-Brexit regulations stabilize.

### f. On-Track Items

- None Identified

### g. Recommendations

- Diversify Sourcing: Identify alternative suppliers in low-risk regions.

- Adjust Schedules: Incorporate buffer times for shipments from high-risk regions.

- Develop Contingency Plans: Prepare for labor disruptions by securing additional inventory or alternative production sites.

- Monitor Geopolitical Developments: Establish a monitoring system for real-time updates on geopolitical tensions. Medium Risk Items:

## 3. Detailed Risk Analysis by Category

### A. Schedule Risk Analysis

#### High Risk Items

- None Identified

#### Medium Risk Items

- LV Switchgear - 400V/5000A Switchboard-1 (3-Sections):

  - Early delivery by 31 days.

  - Risk %: 10.44%.

  - Mitigation Actions: Confirm site readiness, coordinate with supplier, ensure proper storage facilities.

#### Low Risk Items

- Equipment from the USA and India due to political and tariff risks.

### B. Political Risk Analysis

| Country | Political Type | Risk Information | Likelihood (0-5) | Likelihood Reasoning | Publication Date | Citation Title | Citation Name | CitationsURL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| USA-China | Trade Sanctions | Ongoing trade sanctions affecting exports | 4 | High likelihood due to recent escalations | April 2025 | US-China Trade Tensions Escalate | Reuters | Link |
| India-Germany | Tariff Disputes | Disputes over electrical equipment tariffs | 3 | Moderate likelihood due to ongoing negotiations | April 2025 | India-Germany Trade Talks | Bloomberg | Link |
| UK | Regulatory Changes | Post-Brexit regulatory shifts impacting exports | 2 | Low likelihood as changes are stabilizing | April 2025 | UK Post-Brexit Trade | Financial Times | Link |
| Philippines-China | Geopolitical Tensions | Maritime disputes affecting trade routes | 4 | High likelihood due to unresolved tensions | April 2025 | South China Sea Disputes | BBC | Link |
| Malaysia | Labor Strikes | Labor strikes disrupting manufacturing | 3 | Moderate likelihood due to recent strikes | April 2025 | Malaysia Labor Unrest | The Guardian | Link |

Equipment Impact Analysis

- High Risk: USA-China Trade Sanctions and Philippines-China Geopolitical Tensions

- Medium Risk: India-Germany tariff disputes and Malaysia labor strikes.

- Low Risk: UK regulatory changes.

Mitigation Recommendations

- Diversify Sourcing: Reduce dependency on high-risk regions.

- Adjust Schedules: Add buffer times for shipments from high-risk areas.

- Develop Contingency Plans: Prepare for labor disruptions.

## 4. Consolidated Recommendations

- Diversify sourcing to reduce dependency on high-risk regions.

- Adjust schedules to incorporate buffer times for shipments from high-risk regions.

- Develop contingency plans for labor disruptions and geopolitical tensions.

- Monitor geopolitical developments and trade regulations for real-time updates.