# Comprehensive Equipment Schedule Risk Analysis

## 1. Executive Summary

- Overall Risk Levels:

  - Medium Risk: 1 item

  - Low Risk: 2 items

  - On-Track: 0 items

- Key Findings:

  - No high-risk items identified.

  - Medium risk item has a 10.44% risk percentage, requiring mitigation actions.

  - Low risk items have minimal impact but require monitoring.

- Total Equipment Analyzed: 3

## 2. Comprehensive Risk Summary Table

### Executive Summary:

- Total Items Analyzed: 3

- Risk Breakdown:

  - Medium Risk: 1 item

  - Low Risk: 2 items

  - On-Track: 0 items

### Equipment Comparison Table:

| Equipment Code | Equipment Name | P6 Due Date | Delivery Date | Variance (days) | Risk % | Risk Level | Manufacturing Country | Project Country |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | 10.44 | Medium Risk | USA | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | 1.66 | Low Risk | China | Germany |
| 123458 | LV Switchgear - 400V/5000A Switchboard-3 (3-Sections) | 2026-02-27 | 2026-03-07 | 8 | 2.64 | Low Risk | Philippines | Germany |

### High Risk Items:

- None Identified

### Medium Risk Items:

- LV Switchgear - 400V/5000A Switchboard-1 (3-Sections)

  - Variance: -31 days (Ahead of Schedule)

  - Risk Percentage: 10.44%

  - Impact: Early delivery may lead to storage costs and potential misalignment with site readiness.

  - Factors Contributing: Supplier lead time optimization and expedited logistics.

  - Potential Downstream Effects: Increased costs for storage and handling, potential misalignment with installation schedules.

  - Recommended Mitigation Actions:

    - Coordinate with site teams to ensure readiness for early delivery.

    - Engage supplier to confirm delivery timelines and avoid further adjustments.

    - Monitor storage costs and explore temporary storage solutions.

### Low Risk Items:

- LV Switchgear - 400V/5000A Switchboard-2 (3-Sections)

  - Variance: -5 days (Ahead of Schedule)

  - Risk Percentage: 1.66%

  - Impact: Minimal impact expected due to slight early delivery.

  - Factors Contributing: Efficient logistics and supplier adherence to lead times.

  - Potential Downstream Effects: None significant.

  - Recommended Mitigation Actions:

    - Maintain current schedule adherence.

    - Monitor for any changes in delivery timelines.

- LV Switchgear - 400V/5000A Switchboard-3 (3-Sections)

  - Variance: 8 days (Behind Schedule)

  - Risk Percentage: 2.64%

  - Impact: Slight delay may require adjustments to installation schedules.

  - Factors Contributing: Logistics delays and manufacturing lead time.

  - Potential Downstream Effects: Minor adjustments to project timelines.

  - Recommended Mitigation Actions:

    - Monitor logistics closely to avoid further delays.

    - Coordinate with site teams to adjust installation schedules.

### On-Track Items:

- None Identified

## 3. Detailed Risk Analysis by Category

### A. Schedule Risk Analysis

#### Medium Risk Items:

- LV Switchgear - 400V/5000A Switchboard-1 (3-Sections)

  - Variance: -31 days (Ahead of Schedule)

  - Risk Percentage: 10.44%

  - Impact: Early delivery may lead to storage costs and potential misalignment with site readiness.

  - Factors Contributing: Supplier lead time optimization and expedited logistics.

  - Potential Downstream Effects: Increased costs for storage and handling, potential misalignment with installation schedules.

  - Recommended Mitigation Actions:

    - Coordinate with site teams to ensure readiness for early delivery.

    - Engage supplier to confirm delivery timelines and avoid further adjustments.

    - Monitor storage costs and explore temporary storage solutions.

#### Low Risk Items:

- LV Switchgear - 400V/5000A Switchboard-2 (3-Sections)

  - Variance: -5 days (Ahead of Schedule)

  - Risk Percentage: 1.66%

  - Impact: Minimal impact expected due to slight early delivery.

  - Factors Contributing: Efficient logistics and supplier adherence to lead times.

  - Potential Downstream Effects: None significant.

  - Recommended Mitigation Actions:

    - Maintain current schedule adherence.

    - Monitor for any changes in delivery timelines.

- LV Switchgear - 400V/5000A Switchboard-3 (3-Sections)

  - Variance: 8 days (Behind Schedule)

  - Risk Percentage: 2.64%

  - Impact: Slight delay may require adjustments to installation schedules.

  - Factors Contributing: Logistics delays and manufacturing lead time.

  - Potential Downstream Effects: Minor adjustments to project timelines.

  - Recommended Mitigation Actions:

    - Monitor logistics closely to avoid further delays.

    - Coordinate with site teams to adjust installation schedules.

## 4. Consolidated Recommendations

- Medium Risk:

  - Engage supplier to confirm delivery timelines and avoid further adjustments.

  - Coordinate with site teams to ensure readiness for early delivery.

  - Monitor storage costs and explore temporary storage solutions.

- Low Risk:

  - Maintain current schedule adherence.

  - Monitor for any changes in delivery timelines.

- General Recommendations:

  - Implement a proactive monitoring system for logistics and supplier lead times.

  - Develop contingency plans for storage and handling of early deliveries.